PROJECT CHARTER Điều Lệ Dự Án

Document Version: 1.0 (Draft) ¦ Date: 23/02/2026 ¦ Contract: BAWS-2026-EMMA-01

NexaHelix Strategic AI Workspace ¦ Internal R&D

| I. PROJECT IDENTIFICATION / Mô Tả Tổng Thể |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Client / Khách Hàng | Internal — NexaHelix Strategic AI Workspace |
| Project Name / Tên Dự Án | BA Workspace — AI Validation Module (Agent Emma) |
| Contract No. | BAWS-2026-EMMA-01 |
| Contract Value | N/A (Internal R&D) |
| Project Manager (P.M) | Alex |
| Project Owner (P.O) | Paul |
| Project Team / Nhân Sự | Alex (Senior BA), Emma (AI Agent), Paul (Traceability Expert) |
| Location / Địa Điểm | Da Nang, Vietnam |
| Date / Ngày | February 2026 |

| II. KEY CONTACTS / Nhân Sự Phối Hợp |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Role / Vai Trò | Name / Họ Tên | Email | Phone |
| Project Manager | Alex | alex@nexahelix.ai | +84 947 115 711 |
| Traceability Expert | Paul | paul@nexahelix.ai | Internal |
| AI Validation Logic | Emma (AI Agent) | emma.agent@baws.io | System Agent |
| Approved Representative | VINEN.org Representative | contact@vinen.org | N/A |

| III. OBJECTIVES & REQUIREMENTS / Mục Tiêu & Yêu Cầu Dự Án |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Objectives / Mục Tiêu (SMART) - Reduce Rework: Giảm 60–70% thời gian chỉnh sửa yêu cầu (rework) thông qua việc phát hiện mâu thuẫn sớm bằng AI trước tháng 08/2026. - Quality Standardization: 100% yêu cầu được tải lên phải đạt điểm chất lượng >80/100 theo thang đo của Emma trước khi chuyển sang giai đoạn phát triển. - Automated Traceability: Tự động hóa việc tạo Ma trận truy xuất nguồn gốc (RTM) với độ chính xác >90%. 2. Requirements / Yêu Cầu - Hệ thống phải thực hiện chấm điểm yêu cầu dựa trên công thức: Qtotal = (0.4 × SSMART) + (0.35 × SConsistency) + (0.25 × STraceability) - Emma phải có khả năng phân biệt và xử lý Business Rules theo hai cấp độ: Hard Rule (Khóa trạng thái) và Soft Rule (Cảnh báo). - Cung cấp giao diện "Emma's Critique" hiển thị radar chart và các đề xuất chỉnh sửa trực tiếp cho BA. |

| IV. SCOPE OF WORK / Phạm Vi Công Việc |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work Area / Hạng Mục | In Scope / Trong Phạm Vi | Out of Scope / Ngoài Phạm Vi |
| Requirement Scoring Engine | - SMART-format validation - Consistency detection - Traceability scoring - Auto RTM generation (>90% accuracy) | - Manual scoring workflows - Non-BA document types |
| Business Rules Engine | - Hard Rule enforcement (lock state) - Soft Rule warnings to BA | - Legal/compliance rule authoring - External system rule sync |
| Emma's Critique Interface | - Radar chart quality display - Inline edit suggestions for BA - Version diff view | - Mobile UI - Public-facing dashboards |

| V. DELIVERABLES & MILESTONES / Hạng Mục Triển Khai |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Deliverable / Hạng Mục Bàn Giao | Milestone / Giai Đoạn | Deadline |
| 1 | Requirements Scoring Engine — v1 (prototype) | Phase 1 — Engine Build | 30/04/2026 |
| 2 | Business Rules Engine (Hard + Soft Rule logic) | Phase 2 — Rules Engine | 31/05/2026 |
| 3 | Emma's Critique Interface (radar chart + suggestions) | Phase 3 — UI Build | 30/06/2026 |
| 4 | Auto RTM Generation Module (>90% accuracy target) | Phase 4 — Traceability | 31/07/2026 |
| 5 | Final Integration, UAT & Sign-off | Phase 5 — UAT & Launch | 31/08/2026 |

| VI. PAYMENT SCHEDULE / Tiến Độ Thanh Toán |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Note / Lưu Ý | This is an Internal R&D project. No financial payments apply. Budget tracking and resource allocation are managed via the NexaHelix internal resource plan. |

| VII. RISK REGISTER / Rủi Ro Tổng Thể Dự Án |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Risk / Rủi Ro | Mitigation / Phương Án Dự Phòng | Owner / Đơn Vị Xử Lý |
| 1 | AI scoring formula produces inconsistent results across requirement types | - Define test cases per requirement type before Phase 1 - Run weekly calibration sessions with Alex & Emma | Alex (P.M) |
| 2 | Hard Rule logic blocks valid BA workflows, causing process friction | - Shadow-run Hard Rules in read-only mode for 2 weeks before enforcement - Escalation path to Paul for override decisions | Paul (P.O) |
| 3 | RTM accuracy falls below 90% target in complex traceability scenarios | - Benchmark RTM on 3 historical projects before Phase 4 - Define fallback: manual review flag for low-confidence links | Emma / Paul |
| 4 | Scope creep — requests to extend Emma to non-BA document types | - Strict change request process; P.O (Paul) must approve any scope additions - Bi-weekly scope review checkpoint | Paul (P.O) |

| VIII. OTHER NOTES / Lưu Ý Khác |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Emma is an AI Agent — not a human team member. All outputs from Emma must be reviewed and approved by Alex (BA) before being used in project artefacts. - The quality scoring formula (Q_total) is subject to revision after Phase 1 calibration. Any changes require written approval from Paul (P.O). - VINEN.org is an external stakeholder providing domain context. Their representative has observer status only and does not have approval authority over deliverables. - All documents produced under this charter are classified Internal R&D and must not be shared outside NexaHelix without explicit P.O approval. |

| IX. SIGN-OFF / Cam Kết |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Client Representative / Đại Diện Khách Hàng | Project Owner (P.O) | Project Manager (P.M) |
| VINEN.org Representative Signature: ________________ Date: __________ | Paul Traceability Expert / P.O Signature: ________________ Date: __________ | Alex Senior BA / P.M Signature: ________________ Date: __________ |