PRODUCT BACKLOG Danh Mục Yêu Cầu / Requirements Register

Version: 1.0 (Draft) ¦ Date: 23/02/2026 ¦ Methodology: Waterfall ¦

NexaHelix Strategic AI Workspace ¦ Internal R&D ¦ BAWS-2026-EMMA-01

Methodology Note: This project follows a Waterfall methodology. The Product Backlog is used here as a Requirements Register — a phase-ordered, prioritised inventory of all deliverable work items. Items are not iterated; each phase must be signed off before the next begins. Scope changes require a formal Change Request approved by the P.O (Paul).

| 1. DOCUMENT CONTROL / Kiểm Soát Tài Liệu |  |  |  |
| --- | --- | --- | --- |
| Version | Date | Author | Description |
| 1.0 | 23/02/2026 | Alex (Senior BA) | Initial Requirements Register — derived from BRD v1.0 and FRD v1.0 |

| 2. BACKLOG SUMMARY / Tóm Tắt |  |  |  |
| --- | --- | --- | --- |
| Phase | Module | Work Items | Target Date |
| Phase 1 | Requirement Scoring Engine | PB-01 → PB-08 | 30/04/2026 |
| Phase 2 | Business Rules Engine | PB-09 → PB-15 | 31/05/2026 |
| Phase 3 | Emma's Critique Interface | PB-16 → PB-22 | 30/06/2026 |
| Phase 4 | RTM Generator | PB-23 → PB-28 | 31/07/2026 |
| Phase 5 | Integration, UAT & Go-Live | PB-29 → PB-35 | 31/08/2026 |

| 3. PRIORITY & STATUS LEGEND / Chú Giải |  |  |  |  |
| --- | --- | --- | --- | --- |
| P1 — Critical | P2 — High | P3 — Medium | Must complete this phase — blocks next phase if missing | High value but does not block phase gate |

| 4. REQUIREMENTS REGISTER / PRODUCT BACKLOG / Danh Mục Chi Tiết |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ID | Phase | Module | Work Item / Requirement | FR Ref | Effort (d) | Priority | Status |
| PHASE 1 — Requirement Scoring Engine ¦ Target: 30/04/2026 |  |  |  |  |  |  |  |
| PB-01 | Phase 1 | Scoring Engine | Define and document Q_total formula weights (0.4 / 0.35 / 0.25) with P.O sign-off before build begins | FR-01 | 2 | P1-Critical | In Scope |
| PB-02 | Phase 1 | Scoring Engine | Build S_SMART scoring sub-module: evaluate Specific, Measurable, Achievable, Relevant, Time-bound attributes | FR-02 | 5 | P1-Critical | In Scope |
| PB-03 | Phase 1 | Scoring Engine | Build S_Consistency sub-module: cross-reference against full requirement set for contradictions and duplicates | FR-03 | 6 | P1-Critical | In Scope |
| PB-04 | Phase 1 | Scoring Engine | Build S_Traceability sub-module: verify links to business objectives, features, and test cases | FR-04 | 4 | P1-Critical | In Scope |
| PB-05 | Phase 1 | Scoring Engine | Implement Q_total aggregation engine and scoring API endpoint | FR-01 | 3 | P1-Critical | In Scope |
| PB-06 | Phase 1 | Scoring Engine | Implement ≤80/100 gate: block requirement progression and trigger BA notification with dimension breakdown | FR-05 | 3 | P1-Critical | In Scope |
| PB-07 | Phase 1 | Scoring Engine | Build score breakdown dashboard (colour-coded: Green/Amber/Red per dimension) | FR-06 | 4 | P2-High | In Scope |
| PB-08 | Phase 1 | Scoring Engine | Calibration session: weekly review with Alex & Emma post-build to validate scoring consistency across requirement types | FR-01–06 | 2 | P1-Critical | In Scope |
| PHASE 2 — Business Rules Engine ¦ Target: 31/05/2026 |  |  |  |  |  |  |  |
| PB-09 | Phase 2 | Rules Engine | Design and document initial Hard Rule registry (minimum 10 rules) with Paul (P.O) approval | FR-07 | 3 | P1-Critical | In Scope |
| PB-10 | Phase 2 | Rules Engine | Build Hard Rule enforcement engine: detect violations and set requirement status to BLOCKED | FR-07 | 5 | P1-Critical | In Scope |
| PB-11 | Phase 2 | Rules Engine | Build BLOCKED state UI: display banner with Rule ID, description, and remediation steps | FR-08 | 3 | P1-Critical | In Scope |
| PB-12 | Phase 2 | Rules Engine | Design and document initial Soft Rule registry (minimum 10 rules) with Paul (P.O) approval | FR-09 | 3 | P1-Critical | In Scope |
| PB-13 | Phase 2 | Rules Engine | Build Soft Rule advisory engine: generate warnings without blocking progression | FR-09 | 4 | P1-Critical | In Scope |
| PB-14 | Phase 2 | Rules Engine | Build Soft Rule warning UI: dismissible alerts with Rule ID, explanation, and suggested fix; log dismissal reason | FR-10 | 3 | P1-Critical | In Scope |
| PB-15 | Phase 2 | Rules Engine | Shadow-run Hard Rules in read-only mode for 2 weeks before enforcement goes live (Risk #2 mitigation) | FR-07 | 2 | P1-Critical | In Scope |
| PHASE 3 — Emma's Critique Interface ¦ Target: 30/06/2026 |  |  |  |  |  |  |  |
| PB-16 | Phase 3 | Critique UI | Build radar chart component: 3-axis (SMART / Consistency / Traceability), real-time update on edit | FR-16 | 5 | P1-Critical | In Scope |
| PB-17 | Phase 3 | Critique UI | Build inline annotation engine: Emma attaches plain-language suggestions to specific clauses, citing dimension | FR-17 | 5 | P1-Critical | In Scope |
| PB-18 | Phase 3 | Critique UI | Build Accept / Dismiss interaction for inline suggestions with BA confirmation step | FR-17 | 2 | P1-Critical | In Scope |
| PB-19 | Phase 3 | Critique UI | Build requirement summary panel: Q_total, Rule status, RTM link count, last analysis timestamp | FR-19 | 3 | P1-Critical | In Scope |
| PB-20 | Phase 3 | Critique UI | Implement AI-label badge on all Emma outputs — no auto-apply without explicit BA approval | FR-20 | 2 | P1-Critical | In Scope |
| PB-21 | Phase 3 | Critique UI | Build Version Diff view: side-by-side comparison with green additions / red deletions | FR-18 | 4 | P2-High | In Scope |
| PB-22 | Phase 3 | Critique UI | Usability test: new BA must complete onboarding flow within 10 minutes (NFR-05) | FR-16–20 | 2 | P2-High | In Scope |
| PHASE 4 — RTM Generator ¦ Target: 31/07/2026 |  |  |  |  |  |  |  |
| PB-23 | Phase 4 | RTM Generator | Benchmark RTM engine against 3 historical NexaHelix projects before build — document accuracy baseline | FR-15 | 3 | P1-Critical | In Scope |
| PB-24 | Phase 4 | RTM Generator | Build RTM auto-generation engine: link requirements to BOs, Features, Test Cases, Design Components | FR-12 | 8 | P1-Critical | In Scope |
| PB-25 | Phase 4 | RTM Generator | Implement confidence threshold: flag LOW CONFIDENCE links (<90%) for BA review queue | FR-13 | 4 | P1-Critical | In Scope |
| PB-26 | Phase 4 | RTM Generator | Build BA review queue UI: approve / reject low-confidence RTM links with audit log | FR-13 | 3 | P1-Critical | In Scope |
| PB-27 | Phase 4 | RTM Generator | Build RTM export: .xlsx format with confidence scores per link | FR-14 | 3 | P1-Critical | In Scope |
| PB-28 | Phase 4 | RTM Generator | Build in-app RTM matrix view with filter by module, phase, and confidence level | FR-14 | 4 | P2-High | In Scope |
| PHASE 5 — Integration, UAT & Go-Live ¦ Target: 31/08/2026 |  |  |  |  |  |  |  |
| PB-29 | Phase 5 | Integration | Full system integration: Scoring Engine + Rules Engine + Critique UI + RTM Generator | All FRs | 5 | P1-Critical | Pending |
| PB-30 | Phase 5 | Integration | End-to-end performance test: Q_total scoring must return within 5 seconds for 1,000-word requirements (NFR-01) | NFR-01 | 3 | P1-Critical | Pending |
| PB-31 | Phase 5 | Integration | Security audit: verify zero external data leakage from Emma's processing pipeline (NFR-03) | NFR-03 | 3 | P1-Critical | Pending |
| PB-32 | Phase 5 | Integration | Audit trail validation: confirm 100% logging of rule changes, BA actions, score recalculations (NFR-04) | NFR-04 | 2 | P1-Critical | Pending |
| PB-33 | Phase 5 | UAT | UAT with Alex (BA): validate scoring accuracy, rule behaviour, and critique interface across 20 test requirements | All FRs | 5 | P1-Critical | Pending |
| PB-34 | Phase 5 | UAT | UAT sign-off: Paul (P.O) reviews RTM accuracy results and approves go-live | FR-12–15 | 3 | P1-Critical | Pending |
| PB-35 | Phase 5 | Go-Live | Go-live deployment and internal handover documentation — NexaHelix BA Workspace launch | All | 2 | P1-Critical | Pending |

| 5. DEFERRED & OUT-OF-SCOPE ITEMS / Hạng Mục Hoãn & Ngoài Phạm Vi |  |  |
| --- | --- | --- |
| ID | Item | Reason |
| DEF-01 | Mobile / native application UI | Out of scope per Project Charter §IV. No mobile requirement defined. |
| DEF-02 | Public-facing dashboards or external user access | Internal R&D only. External access not permitted per NFR-03. |
| DEF-03 | Legal/compliance rule authoring (external standards) | Requires domain expertise outside project scope. Post-launch consideration. |
| DEF-04 | Synchronization with external CRM or ERP systems | No integration requirement in Charter. Deferred to v2.0 roadmap. |
| DEF-05 | Non-BA document types (design specs, test plans, presentations) | Emma is scoped to BA requirement documents only per Charter §IV. |